## Sheet1
State Estimation					Planning					Motor Control					Sensors					Hardware Setup

			Time Spent					Time Spent					Time Spent					Time Spent					Time Spent
Ball Estimation	6				Movement Planning	5				C++ Classes	DONE				Read Encoder	10				Make 3D model	12
Can't do without hardware															Can't do without hardware
					Shoot Planning	5				Motor Model	DONE				Read Ultrasonic	4				Laser Cut	4
Light sensor localisation	4									Convert Matrix to C++	1				Can't do without hardware
Can't do without hardware					TEST/DEBUG	10				Cant do without measurements					Read Light	6				Assemble	4
Ultrasonic localisation	Done														Can't do without hardware
															Read Infrared	10				Setup Infrared sensors	8
Encoder Localisation	5														Can't do without hardware					Assemble Shooter	10
Can't do without hardware																				Assemble Dribbler	10
										Can't do without hardware
										Shoot Control	5									Debug Hardware	12
										Can't do without hardware					TEST/DEBUG	10
										Dribbler Control	5									Test Sensors	4
Convert to C++	4									Can't do without hardware

Testing / Debugging	10									TEST/DEBUG	10

SUM	29					20					21					40					64	TOTAL	174
																						HOURS PER DAY	4

																						DAYS	43.5